## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket.
As a Helper I want to see, search, and checkout the needs so that I can properly fund them. | Given an invalid user upon login, the system rejects the attempt | Pass | GV, 10/30
| Given a valid used upon login, the system routes to a new address | Pass | GV, 10/30
As a Ufund Manager I want to add a need to the cupboard so that properly update the needs in the cupboard. | Given an admin login, logging in results in the host routing to an admin-specific address | Pass | MF, 10/30
| Given a non-admin login, logging in results in the host routing to the user specific address | Pass | MF, 10/30
| Given an invalid login, logging in fails and does not route | Pass | MF, 10/30
As a user, I want to enter my credentials so that I can log in. | given the ui works, and I log in to the site, I expect to be on a different page | Pass | MF, 10/30
As a user, I want to store my needs in a basket for the sake of organization and ease of use. | Given I am a new user when I look at my basket, it should be empty | Pass | TB, 10/30
| Given I am a known user when I look at my basket, it should have my needs saved there | Pass | TB, 10/30
| Given I am not a user when I look for the basket, I should not be able to see it | Pass | TB, 10/30
As an admin, I want to be able to modify the cupboard of needs so that it can be edited to reflect actual supplies and reality | Given I use admin when I log in, I can edit the cupboard | Pass | TB, 10/30
| Given I do not use admin when I log in, I cannot access the cupboard | Pass | TB, 10/30
As a developer, I want a testable function with unit tests, so that I can make sure my project is working. | Given the program works when I test the program with the unit tests, then it will return a signal to indicate that the program functions. | Pass | GV 10/30
| Given the program does not work when I test the program with the unit tests, then it will return a signal to indicate that the program does not function. | Pass | GV 10/30
As a user I want to be able to move certain smaller quantities of needs from the basket so that I can move only what I need of the needs. | Given a need is in the cupboard, has a quantity of one or more when I add it to the basket, and no need of the same type exists in the basket, it should have one subtracted from its quantity and a new need is created in the basket of the same type, with a quantity of one |  |  | Fail | NOT IMPLEMENTED
Given a need is in the cupboard, has a quantity of one or more when I add it to the basket, and an equal need exists in the basket, it should have one subtracted from its quantity and have one added to the quantity of the need in the basket already
Given a need is in the cupboard and has a quantity of zero when I add it to the basket, nothing should change
Given a need is in the basket and has a quantity of more than one when I remove it from the basket, then the need in the basket should have one subtracted from its quantity and the corresponding need in the cupboard should have one added to its quantity
Given a need is in the basket and has a quantity of one when I remove it from the basket, then the need in the basket should be deleted and the corresponding need in the cupboard should have one added to its quantity
As a user, I want to be routed to an error page so that I can understand when and why something goes wrong | Given I encounter an error on any action, I am routed to an error page |  |  |  | NOT IMPLEMENTED
As a user, I want the ui to look pretty so that I don’t feel like the site is too shady to use. | Given I am any user when I am routed to any page on the site, I expect the page to have some finer details than basic ui |  |  |  | NOT IMPLEMENTED
Given I am any user when I am routed to any page, I expect there to be some level of color-coding for buttons and text
As a user, I want to have more buttons and scrollbars and miscellaneous interactables so that I have a minutely higher quality of life while using the site | Given I am a user when I am searching for needs of a certain range in a quality, I can use the ui to narrow down a search by some range for some quality |  |  |  | NOT IMPLEMENTED
Given I am an admin when I am searching for needs of a certain range in a quality, I can use the ui to narrow down a search by some range for some quality
I ojo knm na
Areaya Haeji Zace